## Sheet1
Task Name | Estimated time (Minutes) | Start Date (MM/dd/yyyy) | End Date (MM/dd/yyyy)
Isomatric Drawing Prepration | 50 | 22/09/2019 | 22/09/2019
Isometric drawing submission to client | 50 | 2019-09-23 | 2019-09-23
IBR Activities
Documents reqd. from client |  | 2019-09-28 | 2019-09-28
Isometric drawing preparation (Ibr office) |  | 2019-09-29 | 2019-09-29
Isometric drawing preparation (Submission Ibr office) |  | 2019-09-30 | 1-10-2019
Work order and work permission letter to Ibr office |  | 2019-10-02 | 2019-10-03
Provisional drawing approval |  | 2019-10-04 | 2019-10-04
Material Inspection preparation |  | 2019-10-05 | 2019-10-07
Weld setup imspection |  | 2019-10-08 | 2019-10-10
Hydro test |  | 2019-10-11 | 2019-10-12
Asbuild drawing submission |  | 2019-10-13 | 2019-10-15
Material procruetment and dispatch
Material indenting |  | 2019-09-24 | 2019-09-24
Material procruetment |  | 2019-09-24 | 2019-09-24
Material in stores |  | 2019-10-04 | 2019-10-06
Material dispatch |  | 2019-10-06 | 2019-10-06
Material checking on site |  | 2019-10-08 | 2019-10-10
Execution
Dismentalling of existing steam line |  | 2019-10-04 | 2019-10-05
Erection of existing steam line |  | 2019-10-06 | 2019-10-10
Fabrication of steam line for vuclunization and richer m/c on tack weld |  | 2019-10-11 | 2019-10-16
Full welding of steam line |  | 2019-10-18 | 2019-10-20
Fabrication of condensate line |  | 2019-10-21 | 2019-10-24
Erection of steam line |  | 2019-11-01 | 2019-11-04
Erection of condensate line |  | 2019-11-05 | 2019-11-12
Handover
Report signing and handing over. |  | 2019-11-13 | 2019-11-13