## Sheet1
Task Name | Estimated time (Minutes) | Start Date (MM/dd/yyyy) | End Date (MM/dd/yyyy)
Requirement Study and Plan | 100 | 16/10/2019 | 16/10/2019
Quotations not to be linked to further processes. (If no quotation is made, still should be able to use the software) | 30 | 16/10/2019 | 16/10/2019
Job card search facility by Employee. | 30 | 16/10/2019 | 16/10/2019
Also, while making JC, facility to add other employee names who visited together for that site (by employee drop down) | 30 | 16/10/2019 | 16/10/2019
Facility to add external Job Card number – 6-7 digits, and it should be unique. Same number cannot be added more than once | 30 | 16/10/2019 | 16/10/2019
Facility to search JC number wise in Jobcard | 30 | 16/10/2019 | 16/10/2019
Facility to add name of employee who added Jobcard, in Show JC | 30 | 16/10/2019 | 16/10/2019
Facility to search by Divisionin Customer master | 30 | 16/10/2019 | 16/10/2019
Facility to search by sub-division in Customer master | 30 | 17/10/2019 | 17/10/2019
Facility to search by section in Customer master | 30 | 17/10/2019 | 17/10/2019
For sub-division, to give facility to add Code, and include code in search | 30 | 17/10/2019 | 17/10/2019
In Job card, facility required to edit or add site name and DTC | 30 | 17/10/2019 | 17/10/2019
Jobcard to have column to add Start time and End time – compulsory fields. | 30 | 17/10/2019 | 17/10/2019
While adding Supply order, it can be locked for a sub-division or section so that it cannot be used for other sub-division or other section. | 30 | 17/10/2019 | 17/10/2019
Facility to add Security Deposit or Bank Guarantee and its details, while adding Supply Order. | 30 | 17/10/2019 | 17/10/2019
Show this on separate page with ‘Pending’ and ‘Closed’ tabs. | 30 | 18/10/2019 | 18/10/2019
After receiving back SD and clearing of BG it should go to closed folder. | 30 | 18/10/2019 | 18/10/2019
Facility to add material code. It should be unique and cannot be repeated. This will be shown in all further records like quotation, SO, Invoice, JC etc. | 30 | 18/10/2019 | 18/10/2019
Developer testing | 100 | 18/10/2019 | 18/10/2019
First Local testing | 120 | 19/10/2019 | 19/10/2019
First Local testing error solved | 120 | 19/10/2019 | 19/10/2019
First Online testing | 120 | 19/10/2019 | 19/10/2019
First online testing error solved | 120 | 19/10/2019 | 19/10/2019
final document submit design | 15 | 19/10/2019 | 19/10/2019