## Sheet1
ENTREMONDE POLYCOATERS, SATPUR MIDC, NASHIK
DATE
SR. NO. | ACTIVITY | time axis 2019-06-19 to 2019-08-24
1 | chimney foundation drawing preparation | D | bar: 2019-06-19
2 | chimney foundation bolt material procurement and processing of foundation bolts | D | bar: 2019-06-20
| material to be indent | D | bar: 2019-06-20
material purchased at R&D | bar: 2019-06-20
3 | Chimney foundation bolt fabrication | D | bar: 2019-06-21 to 2019-06-25
details given to design | bar: 2019-06-21 to 2019-06-25
drawing preparation by design dept. | bar: 2019-06-21 to 2019-06-25
drawing given to production head | bar: 2019-06-21 to 2019-06-25
all details regarding processes on foundation bolts like threading, gussets | bar: 2019-06-21 to 2019-06-25
4 | allocation letter and drawings from thermax | D | bar: 2019-06-23
5 | submission of drgs to client | D | bar: 2019-06-25
6 | foundation bolt and template dispatch | D | bar: 2019-06-26
preparation for transporter arrangement | bar: 2019-06-26
prepare delivery challan | bar: 2019-06-26
7 | PIV 1 | D | bar: 2019-06-26
8 | PIV 2 | bar: 2019-07-04
9 | chimney drawing and cross checking | D | bar: 2019-06-20
details to be given to design dept. | bar: 2019-06-20
10 | chimney mat. Procrutment | D | bar: 2019-06-27
11 | piping material procrutement | D | bar: 2019-07-02
| detailing with isometric drawing | D | bar: 2019-07-02
indent to purchase dept. | bar: 2019-07-02
follow up for dates of material received | bar: 2019-07-02
12 | piping and valves mat. On R&D | bar: 2019-07-15
transport, material storage & checking of material | bar: 2019-07-15
13 | chimney and tank fabrication, ducting | bar: 2019-07-02 to 2019-07-15
details given to design | bar: 2019-07-02 to 2019-07-15
drawing preparation by design dept. | bar: 2019-07-02 to 2019-07-15
drawing given to production head | bar: 2019-07-02 to 2019-07-15
14 | chimney ,tank and material dispatch,strutural support,ducting | bar: 2019-07-16 to 2019-07-18
transport , loading and unloading of vehicle | bar: 2019-07-16 to 2019-07-18
15 | unit and material on site | bar: 2019-07-31
16 | consignment checkup | bar: 2019-08-02
17 | erection of unit and pumps | bar: 2019-07-31
18 | structure fabrication
19 | chimney erection | bar: 2019-07-20 to 2019-07-21
20 | Thermic fluid piping fabrication and erection | bar: 2019-08-03 to 2019-08-12
21 | Pneumatic testing | bar: 2019-08-13 to 2019-08-14
22 | thermic fluid filling | bar: 2019-08-16 to 2019-08-18
23 | Precommisioning | bar: 2019-08-19
24 | Commisioning | bar: 2019-08-20
25 | ENC reports | bar: 2019-08-20
26 | Work completion report. | bar: 2019-08-20
27 | Final billing | bar: 2019-08-21
28 | Reference letter | bar: 2019-08-22

## Sheet2
ENTREMONDE POLYCOATERS, SATPUR MIDC, NASHIK
SR. NO. | ACTIVITY
1 | chimney foundation drawing preparation
foundation details of chimney base plate
hole size 38
size of foundation bolt
design department
2 | chimney foundation bolt material procurement and processing of foundation bolts
indent filling and submit to purchase dept.
Bolt material EN8
3 | Chimney foundation bolt fabrication
Processing on foundation bolt like threading, gussets welding, drilling on template, cutting
4 | allocation letter and drawings from thermax
allocation letter to be kept in W17 cupboard in "allocation letter" file
one set of drawings and O/M manual to be given to client & one set to be kept in B19 cupboard
fill details of all in Service tracker Excel sheet
5 | submission of drawings to client
fill reports of Konark Engineers and take sign and stamp on it
6 | foundation bolt and template dispatch
actual checking of all material with quality and quantity according to drawing
prior information to client for dispatch
preparation of E-way bill invoices and packing slip, delivery challan
make arrangement of vehicle for transportation and LR copy for same
7 | PIV 1
filling of service passport and gathering of data
preparation of TCA reports on Konark Engineers with client sign and stamp
8 | PIV 2
filling of service passport and gathering of data
preparation of TCA reports on Konark Engineers with client sign and stamp
9 | chimney drawing and cross checking
give details to design department according to P&ID
preparation of drawing from design department
cross checking of drawing & revision if any
10 | chimney mat. Procurement
after final cross checking, BOM to be given to purchase department
material receiving date to be taken from purchase department
taking follow up regularly after receiving date expires
11 | piping material procrutement
engineering detailing by project team
indent filling
material receiving date to be taken from purchase department
taking follow up regularly after receiving date expires
12 | piping and valves mat. On rnd
material reciving date
transport for the same from purchase
material on rnd
consignment checking in as per bill and indent.
13 | chimney and tank fabrication, ducting
chimney and tank drawing
material to production
consumables to production from stores
fabrication of the above in shop
14 | chimney ,tank and material dispatch,strutural support,ducting
actual checking of all material with quality and quantity according to drawing
prior information to client for dispatch
preparation of E-way bill invoices and packing slip, delivery challan
make arrangement of vehicle for transportation and LR copy for same
hydra and manpower arrangement
15 | unit and material on site
hydra and manpower arrangement
all invoices from thermax
16 | consignment checkup
packing slip
checking consignment avccording to packing slip
if any short supply complaint on sfdc
preparation of TCA reports on Konark Engineers with client sign and stamp
17 | erection of unit and pumps
foundation checking.
hydra and manpower arrangement
anchor fasting
pump frame fondation
installation according gatp.
18 | structure fabrication
19 | chimney erection
20 | Thermic fluid piping fabrication and erection
21 | Pneumatic testing
22 | thermic fluid filling
23 | Precommisioning
24 | Commisioning
25 | ENC reports
26 | Work completion report.
27 | Final billing
28 | Reference letter

## Sheet5
ENTREMONDE POLYCOATERS, SATPUR MIDC, NASHIK
DATE
SR. NO. | ACTIVITY | time axis 2019-06-19 to 2019-08-24
1 | chimney foundation drawing preparation | D | bar: 2019-06-19
2 | chimney foundation bolt material procurement and processing of foundation bolts | D | bar: 2019-06-20
| material to be indent | D | bar: 2019-06-20
material purchased at R&D | bar: 2019-06-20
3 | Chimney foundation bolt fabrication | D | bar: 2019-06-21 to 2019-06-25
details given to design | bar: 2019-06-21 to 2019-06-25
drawing preparation by design dept. | bar: 2019-06-21 to 2019-06-25
drawing given to production head | bar: 2019-06-21 to 2019-06-25
all details regarding processes on foundation bolts like threading, gussets | bar: 2019-06-21 to 2019-06-25
4 | allocation letter and drawings from thermax | D | bar: 2019-06-23
5 | submission of drgs to client | D | bar: 2019-06-25
6 | foundation bolt and template dispatch | D | bar: 2019-06-26
preparation for transporter arrangement | bar: 2019-06-26
prepare delivery challan | bar: 2019-06-26
7 | PIV 1 | D | bar: 2019-06-26
8 | PIV 2 | D | bar: 2019-07-04
9 | chimney drawing and cross checking | D | bar: 2019-06-20
details to be given to design dept. | bar: 2019-06-20
10 | chimney mat. Procrutment | D | bar: 2019-06-27
11 | piping material procrutement | D | bar: 2019-07-02
| detailing with isometric drawing | D | bar: 2019-07-02
indent to purchase dept. | bar: 2019-07-02
follow up for dates of material received | bar: 2019-07-02
12 | piping and valves mat. On R&D | bar: 2019-07-15
transport, material storage & checking of material | bar: 2019-07-15
13 | chimney and tank fabrication, ducting | bar: 2019-07-02 to 2019-07-15
details given to design | bar: 2019-07-02 to 2019-07-15
drawing preparation by design dept. | bar: 2019-07-02 to 2019-07-15
drawing given to production head | bar: 2019-07-02 to 2019-07-15
14 | chimney ,tank and material dispatch,strutural support,ducting | bar: 2019-07-16 to 2019-07-18
transport , loading and unloading of vehicle | bar: 2019-07-16 to 2019-07-18
15 | unit and material on site | bar: 2019-07-31
16 | consignment checkup | bar: 2019-08-02
17 | erection of unit and pumps | bar: 2019-07-31
18 | structure fabrication
19 | chimney erection | bar: 2019-07-20 to 2019-07-21
20 | Thermic fluid piping fabrication and erection | bar: 2019-08-03 to 2019-08-12
21 | Pneumatic testing | bar: 2019-08-13 to 2019-08-14
22 | thermic fluid filling | bar: 2019-08-16 to 2019-08-18
23 | Precommisioning | bar: 2019-08-19
24 | Commisioning | bar: 2019-08-20
25 | ENC reports | bar: 2019-08-20
26 | Work completion report. | bar: 2019-08-20
27 | Final billing | bar: 2019-08-21
28 | Reference letter | bar: 2019-08-22

## Sheet3
Design Details
|  | Chimney |  |  | Ring man circuit |  |  |  | Structural details
| Top dia | [6 empty] | sr no
| base dia | [6 empty] | 1 | Ring man
height
no. shell
nut bolts
gywire
lighting ar
| d shuckle | [6 empty] | 2 | DE tank
turn buck
temolate
foundation bolt
[8 empty] | 3 | piping
FO tank
Vol.
dia
| ht. |  |  | Ducting |  |  | FO tank service
| no. nozzles |  |  |  |  | Vol.
| inlet nozzle |  |  |  |  | dia
| outlet nozzle |  |  |  |  | ht.
no. nozzles
inlet nozzle
outlet nozzle
Insulation
TF tank
Vol.
dia
ht.
no. nozzles
inlet nozzle
outlet nozzle
Piping
srno | Description | pipe