## BAR CHART
Ace Alcobev CB 20/10.54
| Time → |  | Konark Scope | Ace scope | Jan 20 ( week 1) | [6 empty] | Jan 20 ( week 2) | [7 empty] | Jan 20 ( week 3) | [5 empty] | Jan 20 ( week 4) | [7 empty] | Feb 20 ( week 1) | [5 empty] | Feb 20 ( week 2) | [7 empty] | Feb 20 ( week 3) | [5 empty] | Feb 20 ( week 4) | [6 empty] | March 20 ( week 1) | [6 empty] | March 20 ( week 2) | [6 empty] | March 20 ( week 3) | [6 empty] | March 20 ( week 4) | [6 empty] | Handover week
| Discription ↓ | Status |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Kick off Meeting
Meeting with design , Project, production, Dispatch team
2 | Detaling
A | Piping and consumables | bar: Jan 20 ( week 2) 12
IBR | bar: Jan 20 ( week 2) 12; Jan 20 ( week 3) 18
NIBR | bar: Jan 20 ( week 2) 12; Jan 20 ( week 3) 18
FITTINGS | bar: Jan 20 ( week 2) 12; Jan 20 ( week 3) 18
B | Ducting | bar: Jan 20 ( week 2) 13 to Jan 20 ( week 2) 14
Refering P & ID for ducting sizes | bar: Jan 20 ( week 2) 13 to Jan 20 ( week 2) 14
Ducting from boiler(APH) to MDC | bar: Jan 20 ( week 2) 13 to Jan 20 ( week 2) 14
Ducting from boiler MDC to ID | bar: Jan 20 ( week 2) 13 to Jan 20 ( week 2) 14
Ducting from boiler ID fan to chimney | bar: Jan 20 ( week 2) 13 to Jan 20 ( week 2) 14
C | Manufacturing Items | bar: Jan 20 ( week 3) 16
Chimney 500 dia 30.5 M Heights | bar: Jan 20 ( week 3) 16 to Jan 20 ( week 3) 17
Tank 5 KL | bar: Jan 20 ( week 3) 16 to Jan 20 ( week 3) 17
Electricals | bar: Jan 20 ( week 3) 16 to Jan 20 ( week 3) 17
Cabling from pannel to ID FAN , FD FAN, RAV. | bar: Jan 20 ( week 3) 16; Jan 20 ( week 3) 18
Cabling from pannel to ID FWP 2 nos, Press. Switch,mobrey,rtd 2 nos. | bar: Jan 20 ( week 3) 16; Jan 20 ( week 3) 18
Rtd connection | bar: Jan 20 ( week 3) 18
3 | Design & Document
Layout Drawing | bar: Jan 20 ( week 1) 5; Jan 20 ( week 2) 9
Boiler house layout as per GATP drg. | bar: Jan 20 ( week 1) 5; Jan 20 ( week 2) 9
Study of customers layout. | bar: Jan 20 ( week 1) 5; Jan 20 ( week 2) 9
Layout explanied submitted to client | bar: Jan 20 ( week 1) 5; Jan 20 ( week 2) 9
Chimney Drawing | bar: Jan 20 ( week 2) 8
Details as per po | bar: Jan 20 ( week 2) 8
drg. Preparation as per requirement with all details | bar: Jan 20 ( week 2) 8
template and foundation drg. | bar: Jan 20 ( week 2) 8
Tank Drawing | bar: Jan 20 ( week 3) 17
Details as per po | bar: Jan 20 ( week 3) 17
drg. Preparation as per requirement with all details | bar: Jan 20 ( week 3) 17
Details drg. As per inlet and outlet nozzle,arrangement of float | bar: Jan 20 ( week 3) 17
Structure Drawings | bar: Jan 20 ( week 2) 13; Jan 20 ( week 3) 18
MDC structure | bar: Jan 20 ( week 2) 13; Jan 20 ( week 3) 18
FWT structure | bar: Jan 20 ( week 2) 13; Jan 20 ( week 3) 18
piping , prs , pannel structure | bar: Jan 20 ( week 2) 13; Jan 20 ( week 3) 18
0 | bar: Jan 20 ( week 2) 13; Jan 20 ( week 3) 18
4 | E & C Visit
PIV 1 | bar: Jan 20 ( week 1) 4
Visit to site | bar: Jan 20 ( week 1) 4
checking as per piv 1 requirements | bar: Jan 20 ( week 1) 4
service passport and report fill up and sign | bar: Jan 20 ( week 1) 4
PIV 2 | bar: Jan 20 ( week 1) 4
Visit to site | bar: Jan 20 ( week 1) 4
checking as per piv 2 requirements | bar: Jan 20 ( week 1) 4
service passport and report fill up and sign | bar: Jan 20 ( week 1) 4
Installation guidance | bar: Jan 20 ( week 4) 22; Feb 20 ( week 1) 30
Check all the foundation as per gatp | bar: Jan 20 ( week 4) 22; Feb 20 ( week 1) 30
guidance to installation to client | bar: Jan 20 ( week 4) 22; Feb 20 ( week 1) 30
report fill up and sign | bar: Jan 20 ( week 4) 22; Feb 20 ( week 1) 30
Final foundation checking | bar: Jan 20 ( week 4) 22; Feb 20 ( week 1) 30
0 | bar: Feb 20 ( week 2) 9
5 | Procurment
Piping and consumables | bar: Jan 20 ( week 4) 23
Indend fill and giving to purchase | bar: Jan 20 ( week 4) 23
checvking from our stores | bar: Jan 20 ( week 4) 23
enquiry to 2 to 3 vendors | bar: Jan 20 ( week 4) 23
rates from vendors | bar: Jan 20 ( week 4) 23
quotation and po | bar: Jan 20 ( week 4) 23
followup every 2 days | bar: Jan 20 ( week 4) 23
FEMS Prodcuts | bar: Jan 20 ( week 2) 15
Ordering equipments as per po | bar: Jan 20 ( week 2) 15; Jan 20 ( week 4) 28
order processing in software by sales engg. | bar: Jan 20 ( week 2) 15; Jan 20 ( week 4) 28
SFM | bar: Jan 20 ( week 2) 15; Jan 20 ( week 4) 28
CRS | bar: Jan 20 ( week 2) 15; Jan 20 ( week 4) 28
PRS | bar: Jan 20 ( week 2) 15
Manufacturing Items purchase | bar: Jan 20 ( week 2) 14
Indend fill and giving to purchase | bar: Jan 20 ( week 2) 14
checvking from our stores | bar: Jan 20 ( week 2) 14
enquiry to 2 to 3 vendors | bar: Jan 20 ( week 2) 14
rates from vendors | bar: Jan 20 ( week 2) 14
quotation and po | bar: Jan 20 ( week 2) 14
followup every 2 days | bar: Jan 20 ( week 2) 14
Structural Steel , Fittings, Fastners | bar: Jan 20 ( week 4) 23
Indend fill and giving to purchase | bar: Jan 20 ( week 4) 23
checvking from our stores | bar: Jan 20 ( week 4) 23
enquiry to 2 to 3 vendors | bar: Jan 20 ( week 4) 23
Mat. Like MS chaneel,angle,flats rods etc | bar: Jan 20 ( week 4) 23
Mat. Gaskets,nutbolts , washers , consumales welding rod ,cutting wheels,paint etc | bar: Jan 20 ( week 4) 23
Boiler (Ordered in Dec)
Ordering equipments as per po | bar: Jan 20 ( week 1) 1
order processing in software by sales engg. | bar: Jan 20 ( week 1) 1
| Follow up by sales engg. With thermax |  | will be comimg on 20th feb | bar: Jan 20 ( week 1) 4 to Jan 20 ( week 2) 13
WTP | bar: Jan 20 ( week 3) 17 to Jan 20 ( week 3) 18
Ordering equipments as per po | bar: Jan 20 ( week 3) 17 to Jan 20 ( week 3) 18
order processing in software by sales engg. | bar: Jan 20 ( week 3) 17 to Jan 20 ( week 3) 18
Follow up by sales engg. With thermax | bar: Jan 20 ( week 3) 17 to Jan 20 ( week 3) 18
Electricals cables and Fittings | bar: Jan 20 ( week 2) 15
Indend fill and giving to purchase | bar: Jan 20 ( week 2) 15
checvking from our stores | bar: Jan 20 ( week 2) 15
enquiry to 2 to 3 vendors | bar: Feb 20 ( week 1) 3
0 | Insulation | bar: Feb 20 ( week 1) 3
6 | Material Receipt Date
Piping and consumables | bar: Feb 20 ( week 2) 5
Mat. Entry to store | bar: March 20 ( week 1) 28
Mat. Checking and inspecting by stores with invoice | bar: Feb 20 ( week 1) 2 to Feb 20 ( week 2) 9
If any short fall contact with vendors and taking action | bar: Jan 20 ( week 4) 28 to Feb 20 ( week 1) 1
Test Certificate if any | bar: Feb 20 ( week 3) 14
Rechechked by project engg. Store with tagging. | bar: March 20 ( week 1) 2
0 | FEMS Prodcuts | bar: March 20 ( week 1) 2
Mat. Entry to store | bar: March 20 ( week 1) 2
Mat. Checking and inspecting by stores with invoice | bar: March 20 ( week 1) 2
If any short fall contact with vendors and taking action | bar: March 20 ( week 1) 2
Test Certificate if any | bar: March 20 ( week 1) 2
Rechechked by project engg. Store with tagging. | bar: March 20 ( week 1) 2
Manufacturing Items purchase | bar: March 20 ( week 1) 2
Mat. Entry to store | bar: March 20 ( week 1) 2
Mat. Checking and inspecting by stores with invoice | bar: March 20 ( week 1) 2
If any short fall contact with vendors and taking action | bar: March 20 ( week 1) 2
Test Certificate if any | bar: March 20 ( week 1) 2
Rechechked by project engg. Store with tagging. | bar: March 20 ( week 1) 2
Structural Steel , Fittings, Fastners
Mat. Entry to store
Mat. Checking and inspecting by stores with invoice
If any short fall contact with vendors and taking action
Test Certificate if any
Rechechked by project engg. Store with tagging.
Boiler | bar: Feb 20 ( week 4) 21
Transportation arrangent | bar: Feb 20 ( week 4) 21
documents, bills and invoices,eway bill,thermax bills. | bar: Feb 20 ( week 4) 21
informing to customer | bar: Feb 20 ( week 4) 21
Unloading arrangement | bar: Feb 20 ( week 4) 21
WTP | bar: Feb 20 ( week 4) 23
Transportation arrangent | bar: Feb 20 ( week 4) 23
documents, bills and invoices,eway bill,thermax bills. | bar: Feb 20 ( week 4) 23
informing to customer | bar: Feb 20 ( week 4) 24
Unloading arrangement | bar: Feb 20 ( week 4) 25 to March 20 ( week 1) 26
7 | IBR Visit and Its Documentation | bar: March 20 ( week 1) 3
IBR Folder Receipt Date | bar: March 20 ( week 2) 8
Follow up for ibr folder with thermax | bar: March 20 ( week 2) 8
receipt to our end | bar: March 20 ( week 2) 8
IBR Folder submission | bar: March 20 ( week 2) 8
Ibr folder xerox copy 2nos | bar: March 20 ( week 2) 8
Ibr folder submission to client with report | bar: March 20 ( week 2) 8
original Ibr folder submission to ibr office with letter | bar: March 20 ( week 2) 8
Boiler Registration and Fee Submission | bar: March 20 ( week 3) 14
IBR Drawing Preparation and Submission | bar: March 20 ( week 3) 15
Boiler and Material Inspection | bar: Handover week 30
weld Setup Visit | bar: Handover week 30
Weld Setup Report Submission
Hydro test Visit
Hydro test Report and asbuilt drg submission
MR No Engraving | bar: Jan 20 ( week 4) 29 to Feb 20 ( week 1) 4
8 | Manufacturing | bar: Feb 20 ( week 2) 9 to Feb 20 ( week 2) 11
1 | Work Order for production | bar: Jan 20 ( week 3) 17; Feb 20 ( week 2) 9 to Feb 20 ( week 2) 11
Manufacturing of tank | bar: Jan 20 ( week 4) 27 to Feb 20 ( week 3) 15
8 | Manufacturing of Chimney & Acessories | bar: Jan 20 ( week 4) 27 to Feb 20 ( week 3) 15
Manufacturing of Ducting | bar: Jan 20 ( week 4) 27 to Feb 20 ( week 3) 15; Feb 20 ( week 3) 18 to Feb 20 ( week 4) 19
Supporting Structure | bar: Jan 20 ( week 4) 27 to Feb 20 ( week 3) 15; Feb 20 ( week 4) 21 to Feb 20 ( week 4) 22
9 | Tranportation and Delivery | bar: Feb 20 ( week 4) 19 to Feb 20 ( week 4) 20
Tranportation Arrangemnet | bar: Feb 20 ( week 4) 23
Bills And Invoicing | bar: Feb 20 ( week 4) 23
Delivery of Boiler & accessories
1 | Delivery of Chimney
Piplines & fittings & structural steel
10 | Consignment Checkup ( E & C Visit)
| Material inspection |  |  | All Civil Work | bar: Feb 20 ( week 3) 14 to Feb 20 ( week 3) 18
Mat. Checking as per packing slip | bar: Feb 20 ( week 4) 20
making report and customer sign and stamp | bar: Feb 20 ( week 4) 20
complaint register if any shory fall or damge | bar: Feb 20 ( week 4) 20
11 | Erection | bar: Feb 20 ( week 4) 20 to Feb 20 ( week 4) 22
Foundation of all equipment | bar: Feb 20 ( week 4) 20
Erection of Boiler | bar: Feb 20 ( week 4) 20
Erection of Chimney | bar: March 20 ( week 2) 4 to March 20 ( week 2) 5
Erection of APH | bar: March 20 ( week 2) 8 to March 20 ( week 2) 10
Erection of MDC | bar: March 20 ( week 3) 12
Eretion of FD Fan | bar: March 20 ( week 2) 9 to March 20 ( week 3) 12
Erection of ID fan | bar: March 20 ( week 1) 26 to March 20 ( week 1) 28
Erection of SFM
1 | Erection of CRS
Erection of PRS
10 | Erection of WTP
Erection of Feed Water Tank and Structure | bar: March 20 ( week 2) 6 to March 20 ( week 4) 20
Erection of Ducting (Fliue Gas) | bar: March 20 ( week 3) 17 to March 20 ( week 4) 24
0 | bar: March 20 ( week 4) 22 to Handover week 27
12 | Piping | bar: March 20 ( week 4) 22 to Handover week 27
11 | IBR -Steam line piping | bar: March 20 ( week 4) 18 to March 20 ( week 4) 19
piping mat. As per ibr drawing | bar: March 20 ( week 4) 18 to March 20 ( week 4) 19
Ibr line on tack weld | bar: March 20 ( week 4) 18 to March 20 ( week 4) 19
ibr full welding | bar: March 20 ( week 4) 18 to March 20 ( week 4) 19
ibr steam line from boiler to | bar: March 20 ( week 4) 18 to March 20 ( week 4) 19
NIBR -Steam line piping
Insulation | bar: March 20 ( week 4) 20 to March 20 ( week 4) 24
0 | bar: March 20 ( week 4) 23
13 | Electrification | bar: March 20 ( week 4) 23
12 | Electrical Panel
Electrical cabling | bar: Handover week 25 to Handover week 27
Instrumentation | bar: Handover week 26 to Handover week 27
14 | Commissiong | bar: Handover week 27
Pre commisioning of Boiler | bar: Handover week 27
Checking all piping and erection as per p&I, gatp | bar: Handover week 27
Filling checklist | bar: Handover week 27
chemical boiliing out and slow firing. | bar: Handover week 27
max clean o5 and fuel as per recommendation | bar: Handover week 27
fill boiler with soft water | bar: Handover week 27
Comissioining of Boiler | bar: Handover week 27
ID fan motar rotation, belt tension and alignment with rope or thread,vibration testing. | bar: Handover week 27
all electrical connections | bar: Handover week 27
Fill water in boiler till NWL | bar: Handover week 27
Mobrey level setting, opening the mobrey float,level setting through gauge glass 40% 60% 80%. | bar: Handover week 27
press. Rising gradually then press. Switch setting per client requirement but not below and safty valve setting. | bar: Handover week 27
taking all reading and making report and sign | bar: Handover week 27
Pre commisioning FEMS
PRS checking all the electrical and erection as per drg.
SfM checking all the electrical and erection as per drg.
CRS checking all the electrical and erection as per drg.
Comissioining FEMS | bar: Handover week 30 to Handover week 31
Commisioning as per checklist and procedure CRS | bar: Handover week 30 to Handover week 31
Commisioning as per checklist and procedure CRS | bar: Handover week 30 to Handover week 31
Commisioning as per checklist and procedure CRS | bar: Handover week 30 to Handover week 31
Efficiency Test | bar: Handover week 30 to Handover week 31
Sample point on chimney duct | bar: Handover week 30 to Handover week 31
measuring flue gas parameters with help of kit. | bar: Handover week 30 to Handover week 31
insert probe in samling point and note the reading for o2 and co2 | bar: Handover week 30 to Handover week 31
15 | Document Handover
Service passport
Reference letter
handover
16 | ENC billing (invoicing to thermax)
All sertvice pass port report sign and stamp from customer
billing to thermax and 1 copy to our end
update on thermax enc folder

## Structure Steel
Structural Steel Required
Srno. | Feed Water Tank | MDC | PIPING and ducting Support | Flash vessel,pannel,PRS
ISMC
Size(mm) | 150x75
Qty (nos) | 5
Wt. (kgs) | 342
ISMC
Size(mm) | 100x50 | 100x50 | 100x50 | 100x50
Qty (nos) | 5 | 4 | 2 | 2
Wt. (kgs) | 225 | 180 | 90 | 90
ISA
Size(mm) | 50x5 | 50x5 |  | 40x5
Qty (nos) | 8 | 3 |  | 1
Wt. (kgs) | 180 | 68 |  | 18
Chequre
Size(mm) | 1250x3000
Qty (nos) | 2
Wt. (kgs) | 300
Plate
Size(mm) | 1500x1500 (16mm) | 1000x1000 (10mm) | 1000x1000(10mm) | 1000x1000(12mm)
Qty (nos) | 1 | 1 | 1 | 1
Wt. (kgs) | 282 | 80 | 80 | 80
pipe(#B)
Size(mm) | 25
Qty (nos) | 8
Wt. (kgs) | 80
Rod
Size(mm) | 16
Qty (nos) | 2
Wt. (kgs) | 20
|  |  | Total (kgs) | 2115