## Sheet1
Task Name | Estimated time (Minutes) | Start Date (MM/dd/yyyy) | End Date (MM/dd/yyyy)
Isometric drawing preparation Submission Ibr office | 50 | 2019-09-30 | 10/1/2019
Work order and work permission letter to Ibr office | 50 | 2019-10-02 | 2019-10-03
Provisional drawing approval | 50 | 2019-10-04 | 2019-10-04
Material Inspection preparation | 50 | 2019-10-05 | 2019-10-07
Weld setup imspection | 50 | 2019-10-08 | 2019-10-10
Hydro test | 50 | 2019-10-11 | 2019-10-12
Asbuild drawing submission | 50 | 2019-10-13 | 2019-10-15
Material indenting | 50 | 2019-09-24 | 2019-09-24
Material procruetment | 50 | 2019-09-24 | 2019-09-24
Material in stores | 50 | 2019-10-04 | 2019-10-06
Material dispatch | 50 | 2019-10-06 | 2019-10-06
Material checking on site | 50 | 2019-10-08 | 2019-10-10
Dismentalling of existing steam line | 50 | 2019-10-04 | 2019-10-05
Erection of existing steam line | 50 | 2019-10-06 | 2019-10-10
Fabrication of steam line for vuclunization and richer mc on tack weld | 50 | 2019-10-11 | 2019-10-16
Full welding of steam line | 50 | 2019-10-18 | 2019-10-20
Fabrication of condensate line | 50 | 2019-10-21 | 2019-10-24
Erection of steam line | 50 | 2019-11-01 | 2019-11-04
Erection of condensate line | 50 | 2019-11-05 | 2019-11-12
Report signing and handing over. | 50 | 2019-11-13 | 2019-11-13