## Sheet1
Task Name | Estimated time (Minutes) | Start Date (MM/dd/yyyy) | End Date (MM/dd/yyyy)
Isomatric Drawing Prepration | 480 | 2019-09-22 | 2019-09-22
Isometric drawing submission to client | 180 | 2019-09-23 | 2019-09-23
IBR Activities
Documents reqd. from client | 420 | 2019-09-28 | 2019-09-28
Isometric drawing preparation (Ibr office) | 240 | 2019-09-29 | 2019-09-29
Isometric drawing preparation (Submission Ibr office) | 180 | 2019-09-30 | 1-10-2019
Work order and work permission letter to Ibr office | 180 | 2019-10-02 | 2019-10-03
Provisional drawing approval | 360 | 2019-10-04 | 2019-10-04
Material Inspection preparation | 240 | 2019-10-05 | 2019-10-07
Weld setup imspection | 300 | 2019-10-08 | 2019-10-10
Hydro test | 600 | 2019-10-11 | 2019-10-12
Asbuild drawing submission | 300 | 2019-10-13 | 2019-10-15
Material procruetment and dispatch
Material indenting | 180 | 2019-09-24 | 2019-09-24
Material procruetment | 240 | 2019-09-24 | 2019-09-24
Material in stores | 720 | 2019-10-04 | 2019-10-06
Material dispatch | 240 | 2019-10-06 | 2019-10-06
Material checking on site | 180 | 2019-10-08 | 2019-10-10
Execution
Dismentalling of existing steam line | 240 | 2019-10-04 | 2019-10-05
Erection of existing steam line | 480 | 2019-10-06 | 2019-10-10
Fabrication of steam line for vuclunization and richer m/c on tack weld | 300 | 2019-10-11 | 2019-10-16
Full welding of steam line | 720 | 2019-10-18 | 2019-10-20
Fabrication of condensate line | 1440 | 2019-10-21 | 2019-10-24
Erection of steam line | 720 | 2019-11-01 | 2019-11-04
Erection of condensate line | 2880 | 2019-11-05 | 2019-11-12
Handover
Report signing and handing over. | 240 | 2019-11-13 | 2019-11-13