## Sheet1
Task Name | Estimated time (Minutes) | Start Date (MM/dd/yyyy) | End Date (MM/dd/yyyy)
Requirement Study and Plan | 120 | 16/10/2019 | 16/10/2019
Quotations not to be linked to further processes. (If no quotation is made, still should be able to use the software) | 30 | 17/10/2019 | 17/10/2019
Job card search facility by Employee. Also, while making JC, facility to add other employee names who visited together for that site (by employee drop down | 100 | 17/10/2019 | 17/10/2019
Facility to add external Job Card number – 6-7 digits, and it should be unique. Same number cannot be added more than once | 130 | 17/10/2019 | 18/10/2019
Facility to search JC number wise in Job card | 70 | 18/10/2019 | 18/10/2019
Facility to add name of employee who added Job card, in Show JC | 100 | 18/10/2019 | 18/10/2019
Facility to search by Division, sub-division, section in Customer master | 210 | 18/10/2019 | 19/10/2019
For sub-division, to give facility to add Code, and include code in search | 140 | 19/10/2019 | 22/10/2019
In Job card, facility required to edit or add site name and DTC | 160 | 22/10/2019 | 22/10/2019
Job card to have column to add Start time and End time – compulsory fields. | 100 | 23/10/2019 | 23/10/2019
Facility to add Security Deposit or Bank Guarantee and its details, while adding Supply Order. Show this on separate page with ‘Pending’ and ‘Closed’ tabs. After receiving back SD and clearing of BG it should go to closed folder. | 300 | 23/10/2019 | 24/10/2019
Facility to add material code. It should be unique and cannot be repeated. This will be shown in all further records like quotation, SO, Invoice, JC etc. | 150 | 24/10/2019 | 25/10/2019
While adding Supply order, it can be locked for a sub-division or section so that it cannot be used for other sub-division or other section. | 60 | 25/10/2019 | 25/10/2019
After receiving back SD and clearing of BG it should go to closed folder. | 60 | 25/10/2019 | 25/10/2019
Developer testing | 60 | 25/10/2019 | 25/10/2019
First Local testing | 120 | 26/10/2019 | 26/10/2019
First Local testing error solved | 120 | 26/10/2019 | 26/10/2019
First Online testing | 100 | 26/10/2019 | 26/10/2019
First online testing error solved | 120 | 26/10/2019 | 26/10/2019
final document submit design | 15 | 26/10/2019 | 26/10/2019