## Sheet1
sr.no
1 | Activity | Unit allocation letter and drawing handover to client.
Inform to client about visit take meeting date & time.
Take all documents and drawing from office
Give guidance of all drawings to client
Foundation marking and location of unit done
Make site visit report and take sign and stamp of client.
| Activity | PIV I
Inform to client about PIV I visit .
Take service passport from office.
Visit to site and meet to concern parson.
check foundation status .
Fill the passport check list.
Make TCA service report also take sign and stamp of client.
| Activity | PIV II
Inform to client about PIV II visit .
Take service passport from office.
Visit to site and meet to concern person.
Check foundation status.
Fill the passport checck list.
Make TCA service report also take sign and stamp of client.
| Activity | Consignment check up
Inform to client about consignment check up visit .
Inform to client for case opening tools.
Take service passport and packing slip from office.
Visit to site meet to concern person.
Open all cases with cilent concern person.
Check all cases as per packing slip.
Fill the passport cheack list.
If any short and damage supply found . Not in servis passport ans servis report.
Make TCA service report also take sign and stamp of client.
| Activity | Fabrication of Chimney
Chimney fabrication
Check P.O for required chimney type (like. Self/supported/guy wire/structure supported)
Give all the details to design team for design of chimney.
Ensure and check the drawing
Check all drawing as per P.O and standerd point.
Follow up with production team.
| Activity | Fabrication of Tank
Check P.O for riquired tank.
Give the all details to design team for design the tank.
After completion of drawing give drawing details to production team for manf.
Check and inspect the tank as per drawing.
| Activity | Fabrication of Ducting
Check P.O for specification of ducting.
Give all the details to design team for design the ducting.
Ensure all drawing work start.
Check all drawing as per P.O and standerd point.
Follow up with production team.
| Activity | Chimney installation
Inform to client for hydra/crane.
Check foundation bolt freeness.
Check availability of road for approch to site.
Assembly of chimney shell.
Check alignment of chinmney according to drawing.
| Activity | Unit installation
Inform to client for hydra/crane.
Check foundation bolt and fasteners
check availability of road for approch to site.
Check alignment of unit with drawing.
| Activity | D/E,Fuel tank structure fabrication
Check availability of structure at site.
C |  | Check availability of structure at site.
C |  | Check availability of consumables at site.
Start work of stucture fabrication.
Check structure with drawing.
| Activity | D/E,Fuel tank structure installation.
Inform to client for hydra/crane.
Check foundation bolt and fasteners.
Check availability of road for approch to site.
Check alignment of foundation according drawing.
D/E,Fuel tank structure installation done.
| Activity | D/E,Fuel tank installation.
Inform to client for hydra/crane.
Check foundation bolt freeness.
Check availability of road for approch to site.
Check alignment of structure with drawing.
D/E,Fuel tank installation done.
| Activity | T.F circulation pump.
Inform to client for hydra/crane.
Check foundation of pump with drawing.
Check foundation bolt fastener
T.F circulation pump installation done.
| Activity | Ducting installation.
Inform to client for hydra/crane/ chain pully .
Check readyness of ducting with drawing.
Check flanges diamentions with drawing.
Ducting installation done.
| Activity | Supply header fabrication/installation.
Check availeblity of Material at site. Like pipe, flange,reducer etc.
Give the process line drawing to contractor.
Check availeblity of consumebles at site.
Fabrication/installation work start.
| Activity | Return header fabrication/installation .
Check availability of Material at site. Like pipe, flange,reducer etc.
Give the process line drawing to contractor.
Check availability of consumebles at site.
Fabrication/installation work start.
| Activity | Heater coil installation .
Check availability of coil at site.
Give the coil line drawing to contractor.
Check availeblity of consumebles at site.
Make tapping along with coil installation
Give proper support to coils.
Heater coil installation .
| Activity | Leak test of piping .
Inform to client about the leack test of pipe line.
Give riquired material list to client for leack test of pipe line.
Check all material as per given list to client .
Place dummy at riquired joint in pipe line.
Check all dummy installation done.
Mount pressure gauge on pipe line .
Take pressure in line.
Spray soap water on every joint .
Check welding joint.
Release the pressure .
| Activity | T.F oil filling in piping piping .
Inform to client about the oil filling in pipe line.
Inform to client for arrenging T.F barrel at oil filling location.
Remove all dummy into the T.F line.
Start oil filling in system.
Fill the oil at 20% of total hold up of D/E tank. And fullfill all T.F line.
| Activity | Pre Commisioning
Check all parameters as per list.
Electrical conections
Piping as per P& ID
Availability of fuel.
Availability of electricity
| Activity | Commisioning.